Glossary:

MVP: minimal viable product
ARTA: shorthand for the risk mitigation strategies
PSI: potentially shippable increment
Feature: same as backlog item
Product backlog item: a planned feature
Sprint backlog item: a feature being worked on in a past or current sprint
DoD: definition of done: a measure of implementation quality has all the features previously agreed upon been implemented + tested + are they working without errors.
Skateboard: Proof of concept version demonstrating viability of a complete project.
Wheel: Proof of concept of a (small) part of the project, parts of which are thus unimplemented. This must be individually testable and runnable.
CR: code review
RA: risk assessment
RMP: Risk mitigation plan

Capstone Assignment 1

| Initial project plan [10% of total mark] Do not edit this document after submission to Amathuba |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project name: | ViewScope |  |  |  |  |
| Team nickname | Swapchain |  |  |  |  |
| Team names (first/last) | Adam |  | Kira |  | Azaam |
|  | Foflonker |  | Webb |  | Holdman |
| Student numbers | FFLADA001 |  | WBBKIR002 |  | HLDAZA001 |
| Project description 1 or 2 lines | Build and interactive interface for analyzing the qualities of drone flight paths. The user interface must be responsive and easy to use. The user can inspect if a surface is observed from enough angles, often enough, close enough. The application will allow for easy visualisation of data findings. It will also allow the user to intervene in the path planning by adding/removing cameras. |  |  |  |  |
| Planned programming language(s) | Python, Shell/Bash |  |  |  |  |
| Git url | https://github.com/Schmepp/viewscope.git |  |  |  |  |
| Sprint length | 2 weeks |  |  |  |  |
| Describe non-backlog/non-coding work (filling in forms is not 'work') |  |  |  |  |  |
| Work item 1 | Repo initialization & CI/CD pipelines |  |  |  |  |
| Person responsible | Adam |  |  |  |  |
| Initialize a git repository. Implement CI linting using Ruff. Add static code analysis and type checking using Ty. The linting workflow will run on PR, and all linting issues must be fixed before merging. CI will not autofix issues, instead it will report issues to developers, that way each individual issue can be reviewed by the developer and actioned correctly. Implement CI testing using PyTest. All unit tests are to be written to the tests/ folder and tests are run in CI on PR pushes to main. Implement pytest-coverage. Implement a minimum test coverage threshold of 70% of the codebase. Unit tests are to be manually written but testing and reporting will be fully automated. |  |  |  |  |  |
| Work item 2 | Set up Trello for backlog tracking |  |  |  |  |
| Person responsible | Adam |  |  |  |  |
| Create a Trello board and add all members. Add the resource folder to a card. Create checkboxes for sprint 1 backlogs: Repo init, Review Resource folder, Mitigate from GitLab to GitHub, VI code listing, CI testing and code analysis. Add deadlines to the calendar on Trello, Assignment 1, 2 and 3 due date along with prototypes and sprint 1 deadlines. Keep Trello board updated with changes that may occur such as an extended due date or missed deadlines from developers. |  |  |  |  |  |
| Work item 3 | Research and design of User Interface |  |  |  |  |
| Person responsible | Kira |  |  |  |  |
| Explore existing 3D navigating platforms such as blender. Decide on a method to use to traverse 3D space from a 2D interface (a computer screen). Read about UI design and application responsiveness, e.g. a loading bar to communicate to the user that the program is still running. |  |  |  |  |  |
| Work item 4 | Researching VTK |  |  |  |  |
| Person responsible | Azaam |  |  |  |  |
| Find and read the documentation on the VTK framework. https://docs.vtk.org/en/latest/ Read about the pipeline model of VTK that goes from Data Source to filters, to a mapper then an actor, a render and then to a render window. Evaluate where the output from viewscope_library API meets the VTK framework and what missing links/classes need to be in place for seamless interaction. |  |  |  |  |  |
| Work item 5 | Reviewing the viewscope_core library |  |  |  |  |
| Person responsible | Kira |  |  |  |  |
| Built an interactive website to aid the development process. Site includes full explanations, checklists, a knowledge quiz and a full breakdown of requirements: https://viewscopepreview.pages.dev |  |  |  |  |  |
| Work item 6 | UX feedback |  |  |  |  |
| Person responsible | Azaam |  |  |  |  |
| Profile the application. Perform Alpha testing. Review our design against the HCI guidelines. |  |  |  |  |  |
| Work item 7 | Reviewing application for completeness and correctness |  |  |  |  |
| Person responsible | Kira |  |  |  |  |
| Ensure all data points are accounted for. Review visualisation of the weights and answer questions such as “It is possible for this camera to observe this target.” |  |  |  |  |  |
| Describe Risk 1 | Team member is unavailable due to illness, etc. do not remove or alter this risk. |  |  |  |  |
| Likelihood | Unlikely | Impact |  | Expensive |  |
| ARTA strategy | Transfer |  |  |  |  |
| Mitigations | Implement a clear back-up plan. Create back-up roles, and assign to members who are knowledgeable and skilled in the field of the unavailable member’s task. |  |  |  |  |
| Describe Risk 2 | The use of AI leads to us not learning the concepts nor tools properly. |  |  |  |  |
| Likelihood | Unlikely | Impact |  | Expensive |  |
| ARTA strategy | Transfer |  |  |  |  |
| Mitigations | Write an AI usage document, defining strict boundaries and expectations on the use of AI between team members. Find a compromise on the amount, the frequency, and the fields where it could and shouldn’t be used. |  |  |  |  |
| Describe Risk 3 | Development phase of User Interface may extend by 3 days due to poor initial planning |  |  |  |  |
| Likelihood | Likely | Impact |  | Cheap |  |
| ARTA strategy | Reduce |  |  |  |  |
| Mitigations | Spend an extra day on planning the UI, gathering feedback from members and the client, before starting any development. |  |  |  |  |
| Describe Risk 4 | Release of MVP is delayed by 1 week due to complexity in implementing the VTK framework. |  |  |  |  |
| Likelihood | Unlikely | Impact |  | Expensive |  |
| ARTA strategy | Transfer |  |  |  |  |
| Mitigations | Continuously perform deep/full integration tests on the VTK framework, at least once every three days. |  |  |  |  |
| Describe Risk 5 | Adding too many complex features that aren’t in scope |  |  |  |  |
| Likelihood | Likely | Impact |  | Expensive |  |
| ARTA strategy | Avoid |  |  |  |  |
| Mitigations | Apply YAGNI throughout the development process. |  |  |  |  |
| Describe Risk 6 | Less time spent on development during test periods, which delay the delivery of MVP by 1 week. |  |  |  |  |
| Likelihood | Likely | Impact |  | Expensive |  |
| ARTA strategy | Avoid |  |  |  |  |
| Mitigations | Review the schedule exactly one week before test-week starts. Break larger,longer activities into smaller, shorter activities. |  |  |  |  |
| Describe Risk 7 | Major feature rework needed if client feedback toward initial presentation shows dissatisfaction |  |  |  |  |
| Likelihood | Likely | Impact |  | Expensive |  |
| ARTA strategy | Avoid |  |  |  |  |
| Mitigations | Spend an extra day or two, on further understanding the client’s requirements. Highlighting core features. Conduct internal meetings to make sure every team member understands the requirements, and has constructive plans to meet those requirements. |  |  |  |  |
| Project backlog items |  |  |  |  |  |
| Add as many backlog items as needed |  |  |  |  |  |
| Backlog item 1 |  |  |  |  |  |
| Name | Hello, World! |  |  |  |  |
| Description | Simple working application with all provided files/libraries linked. |  |  |  |  |
| Priority | High |  |  |  |  |
| Main developer | Adam |  |  |  |  |
| Estimated time | Half-week |  |  |  |  |
| Acceptance criteria (DoD): |  |  |  |  |  |
| Functionality | Each member can clone the repository into their own laptop. Small test files such as a hello world .py file may exist to ensure a secure python environment is set up. A requirements.txt file can start to be added to. |  |  |  |  |
| Test cases | Check that cloning works, pushing to the repo works. |  |  |  |  |
| Client remarks |  |  |  |  |  |
| Approved by client | signature |  |  |  |  |
| Backlog item 2 |  |  |  |  |  |
| Name | GUI implementation with VTK |  |  |  |  |
| Description | The first implementation of the GUI |  |  |  |  |
| Priority | High |  |  |  |  |
| Main developer | Azaam |  |  |  |  |
| Estimated time | 2 weeks |  |  |  |  |
| Acceptance criteria (DoD): |  |  |  |  |  |
| Functionality | Users can use two buttons that rotate left and right 90 degrees around the model and an option to switch from textured mesh to just target values along with a button that allows a screenshot or image of the window to be taken. User can spawn cameras by clicking on a button. |  |  |  |  |
| Test cases | Render the Kiri building and navigate 360 degrees around it. |  |  |  |  |
| Client remarks |  |  |  |  |  |
| Approved by client | signature |  |  |  |  |
| Backlog item 3 |  |  |  |  |  |
| Name | Scene rendering |  |  |  |  |
| Description | First fully-working implementation of scene rendering. |  |  |  |  |
| Priority | High |  |  |  |  |
| Main Developer | Kira |  |  |  |  |
| Estimated time | 1 week |  |  |  |  |
| Acceptance criteria (DoD): |  |  |  |  |  |
| Functionality | Render the full scene of the Kiri building from the scaffold/data/kiri/ into a render window. The GUI must be able to display the model as a triangle mesh with texture, an object (.obj file) and as a mass of its target values. |  |  |  |  |
| Test cases | Render the 3D image. Render a 3D image over Kiri. This can be found on Free3D.com |  |  |  |  |
| Client remarks |  |  |  |  |  |
| Approved by client | signature |  |  |  |  |
| Backlog item 4 |  |  |  |  |  |
| Name | Camera placement |  |  |  |  |
| Description | Implement camera picking and placement |  |  |  |  |
| Priority | Middle |  |  |  |  |
| Main Developer | Adam |  |  |  |  |
| Estimated time | Half-week |  |  |  |  |
| Acceptance criteria (DoD): |  |  |  |  |  |
| Functionality | Users must easily be able to place a camera in 3D space. see backlog 11 |  |  |  |  |
| Test cases | See backlog 11 |  |  |  |  |
| Client remarks |  |  |  |  |  |
| Approved by client | signature |  |  |  |  |
| Backlog item 5 |  |  |  |  |  |
| Name | VTK implementation |  |  |  |  |
| Description | Implement relevant VTK gizmos & visualizations. |  |  |  |  |
| Priority | Middle |  |  |  |  |
| Main Developer | Kira |  |  |  |  |
| Estimated time | 1 week |  |  |  |  |
| Acceptance criteria (DoD): |  |  |  |  |  |
| Functionality | Implementing & initializing VTK and ensuring all required visualization methods, tools and other gizmos are working and available for use. |  |  |  |  |
| Test cases | Visual inspection of the tools/gizmos and control over them via mouse+keyboard inputs. |  |  |  |  |
| Client remarks |  |  |  |  |  |
| Approved by client | signature |  |  |  |  |
| Backlog item 6 |  |  |  |  |  |
| Name | Load and validate the data package |  |  |  |  |
| Description | Through the library loaders, failing to open a file will be closed with an actionable message on any malformed file rather than continuing with partial data. |  |  |  |  |
| Priority | Middle |  |  |  |  |
| Main Developer | Azaam |  |  |  |  |
| Estimated time | 1/7 week |  |  |  |  |
| Acceptance criteria (DoD): |  |  |  |  |  |
| Functionality | Attempting to open a corrupted file will result in an error message and not crash the program. Attempting to display a textured model where no texture is provided will result in an un-textured model. Attempting to open an incompatible file type will result in the appropriate error message. |  |  |  |  |
| Test cases | Open a corrupted file, open a file that is incompatible with the software such as an html file, remove textures from the objects folder and try to render it with texture. |  |  |  |  |
| Client remarks |  |  |  |  |  |
| Approved by client | signature |  |  |  |  |
| Backlog item 7 |  |  |  |  |  |
| Name | Pick a surface target |  |  |  |  |
| Description | Picking means clicking in the 3D view and working out what was clicked. Clicking the surface selects the nearest target, marks it, and reveals every camera that observes it, in the 3D scene and in a panel listing the camera identifiers with their values. |  |  |  |  |
| Priority | Middle |  |  |  |  |
| Main Developer | Adam |  |  |  |  |
| Estimated time | 1 week |  |  |  |  |
| Acceptance criteria (DoD): |  |  |  |  |  |
| Functionality | Clicking anywhere on the surface selects the nearest target to the click point. The selected target will be marked as a different colour. Every camera that observes the selected target is highlighted in the 3D scene and listed in a camera panel with its identifier and associated values. Clicking on empty space will result in the surface target no longer being selected. |  |  |  |  |
| Test cases | Click on a surface target and verify with the (target,camera) pairs that the displayed camera IDs are consistent. Click on empty space to ensure the target point is deselected. |  |  |  |  |
| Client remarks |  |  |  |  |  |
| Approved by client | signature |  |  |  |  |
| Backlog item 8 |  |  |  |  |  |
| Name | Visualise the sector decomposition |  |  |  |  |
| Description | Visualise the sector decomposition of a single selected target. One point per observer, placed by direction, radius carrying distance, a reference ring at the preferred distance, coloured by sector, with the angular diversity figure shown. The sector count must be switchable between four and eight. |  |  |  |  |
| Priority | Middle |  |  |  |  |
| Main Developer | Kira |  |  |  |  |
| Estimated time | ¼ week |  |  |  |  |
| Acceptance criteria (DoD): |  |  |  |  |  |
| Functionality | The plot renders one point per observer of the currently selected target and updates when the selection changes. The sector control switches between 4 and 8, and the colouring, sector boundaries recompute accordingly. |  |  |  |  |
| Test cases | Visual inspection on the coloured targets. |  |  |  |  |
| Client remarks |  |  |  |  |  |
| Approved by client | signature |  |  |  |  |
| Backlog item 9 |  |  |  |  |  |
| Name | Visualise the weights |  |  |  |  |
| Description | Colour the observers by weight in the 3D scene and mark the best camera in each sector. Add a bar chart of the best weight per sector with the average shown, so empty sectors read as gaps, and a panel breaking a selected camera into its distance and viewing-angle factors. All of these views must be linked in both directions with the 3D scene and the list. |  |  |  |  |
| Priority | Middle |  |  |  |  |
| Main Developer | Azaam |  |  |  |  |
| Estimated time | 1 week |  |  |  |  |
| Acceptance criteria (DoD): |  |  |  |  |  |
| Functionality | Clicking on a button enables the viewpoints with their coloured weights to be displayed. Highlight the best camera in each sector. A panel displays any selected camera’s distance and angle viewing factors. Clicking on empty space hides the coloured weights,and hides the camera's factors in the panel. |  |  |  |  |
| Test cases | Verify responsiveness of the button. Visual inspection on the coloured weights, and camera’s factors in the panel. Check whether weights and the camera’s factors are hidden, after clicking on empty space. |  |  |  |  |
| Client remarks |  |  |  |  |  |
| Approved by client | signature |  |  |  |  |
| Backlog item 10 |  |  |  |  |  |
| Name | Display live visibility into the tool, see backlog item 4 |  |  |  |  |
| Description | The library function that decides which surface targets a camera can see is provided, occlusion included. Call this correctly for every camera the user adds or moves, keep its input geometry and camera model exactly as shipped, cache the result, and prove your wiring is right by recomputing one shipped viewpoint and matching the packaged visibility for it exactly. The heavy call must never run on the interface thread. |  |  |  |  |
| Priority | Middle |  |  |  |  |
| Main Developer | Adam |  |  |  |  |
| Estimated time | Half-week |  |  |  |  |
| Acceptance criteria (DoD): |  |  |  |  |  |
| Functionality | The shipped visibility function is called whenever a camera is added, moved, or has its parameters changed, and for no other reason. All calculations must be done by the API. Results are cached per camera configuration. If camera changes are not saved then the cached results are removed upon exit of the application. Moving a camera to a previous position serves the cached result rather than recomputing. The visibility call runs off the interface thread. UI must remain responsive. Computation failures must not crash the UI or result in a silent return. |  |  |  |  |
| Test cases | Move a camera, let the API recompute its parameters and then move it back to its previous position. Add a new camera where an existing camera already lies. Trigger a visibility computation on a large scale scene and observe whether or not the UI remains responsive. Check that no stale result is ever observed by a camera. |  |  |  |  |
| Client remarks |  |  |  |  |  |
| Approved by client | signature |  |  |  |  |
| Backlog item 11 |  |  |  |  |  |
| Name | Highlight the visible surface targets of a selected camera. |  |  |  |  |
| Description | Highlight the visible surface targets of the selected camera in the 3D scene, so the user can see at a glance what that camera covers. Occluded targets must never be highlighted. This will include changing the colour of targets that are in the view of said selected camera. |  |  |  |  |
| Priority | High |  |  |  |  |
| Main Developer | Kira |  |  |  |  |
| Estimated time | 2 weeks |  |  |  |  |
| Acceptance criteria (DoD): |  |  |  |  |  |
| Functionality | Select a camera and observe which targets are in the camera's view. Highlight targets that the camera can see. Allow the user to rotate the model to observe all targets, both highlighted and non-highlighted. |  |  |  |  |
| Test cases | Ask if it logically makes sense for that camera to be able to see those targets. Check correctness against all the highlighted targets and the (target, camera) pairs. |  |  |  |  |
| Client remarks |  |  |  |  |  |
| Approved by client | signature |  |  |  |  |
| Backlog item 12 |  |  |  |  |  |
| Name | Build the production user interface with VTK |  |  |  |  |
| Description | Extend the MVP GUI. GUI with at least these panels, dockable and resizable: the 3D viewport, which is the window the scene is drawn in, the viewpoint list, a target detail panel with the weight factor breakdown, the sector plot, the sector bar chart, a metrics panel, and a parameter panel carrying the weak-observation threshold, the safe distance and the sector count with sensible defaults already set. |  |  |  |  |
| Priority | Middle |  |  |  |  |
| Main Developer | Azaam |  |  |  |  |
| Estimated time | 1 week |  |  |  |  |
| Acceptance criteria (DoD): |  |  |  |  |  |
| Functionality | A responsive GUI that users can easily navigate with little to no frustration. The GUI must include all features written in the backlogs. |  |  |  |  |
| Test cases | Dock, undock, float, resize, and close each panel in turn. Include a sensible default layout that users can reset to at any time without losing data. |  |  |  |  |
| Client remarks |  |  |  |  |  |
| Approved by client | signature |  |  |  |  |
| Backlog item 13 |  |  |  |  |  |
| Name | Keep the interface responsive |  |  |  |  |
| Description | Graded against fixed thresholds. Navigation must not drop frames, every click must give visible feedback within 0.2 seconds, and anything over 1 second must show progress and offer cancellation while the rest of the interface stays usable. This needs threads, and separate processes where the library renderer is involved, with clean shutdown. Caching, incremental update and deferred recomputation must be designed and implemented. |  |  |  |  |
| Priority | Middle |  |  |  |  |
| Main Developer | Adam |  |  |  |  |
| Estimated time | Half-week |  |  |  |  |
| Acceptance criteria (DoD): |  |  |  |  |  |
| Functionality | Target framerate held. Every interaction produces visible feedback within 0.2 seconds. Any operation exceeding 1 second must give the user visual feedback that it is currently still processing the request. All worker threads and child processes must be shut down clearly on cancellation and exit. No orphaned, or zombie processes must be left. Ensure a safe state. |  |  |  |  |
| Test cases | Kill the application while the render thread is in process and check which ps -f if any orphaned child processes remain. Evaluate time of a new calculation vs time of a calculation that has recently been cached. Incremental update test: Change one target in a large dataset and ensure that only the affected region is recomputed and redrawn. |  |  |  |  |
| Client remarks |  |  |  |  |  |
| Approved by client | signature |  |  |  |  |
| Add more backlog items as needed. A backlog item must always be completable in a single sprint. Remember: these are all backlog items for the entire project. During the project new items may be added or removed as needed, but only in consultation with the client! |  |  |  |  |  |
| GenAI declaration |  |  |  |  |  |
| Did you use GenAI | Yes |  |  |  |  |
| Describe use | Describe the nature and extent of GenAI use and the specific model used. You are allowed to use GenAI, but you must adhere to the GenAI policy shown on the CSC3003S Amathuba site. Claude Opus 5 was used (with permission from file owners) to create a website that aids programmers by keeping track of code requirements, explaining concepts, and testing them on their knowledge of the API. Prompt that was used: “Create an interactive website that clearly explains the ViewScope library to help developers” |  |  |  |  |
| Add any diagrams or analysis as requested by your client e.g.: entity-relationship diagram for a database application or: data flow diagram for a data-oriented-application |  |  |  |  |  |
| Add any citations as needed |  |  |  |  |  |
| Schroeder, Will; Martin, Ken; Lorensen, Bill (2006), The Visualization Toolkit (4th ed.), Kitware, ISBN 978-1-930934-19-1. charliermarsh (2022). Astral Docs. [online] Astral.sh. Available at: https://docs.astral.sh/uv/ [Accessed 9 Aug. 2026]. |  |  |  |  |  |

Sector decomposition. The cameras observing one surface target, coloured

by their directional sector relative to the target normal.